## Services
Ministry of Labour & Employment, DGE&T
National Project Implementation Unit (NPIU) | [28 empty] | Status: | Updated
Procurement Activity Schedule: Consulting Services during the Project i.e. upto December 2012 | [28 empty] | Printed: | 2009-12-07 10:15
Number | PP Status | Category Component- wise | Package No. | Contract Ref. | Description of Services | Estimate Cost in USD | Method of Selection (QCBS/QBS/CQS/LCS/FBS/SSS) | Post/Prior Review Status | Preparation of TOR, cost estimate, sanction etc., | Transmit TOR and cost estimate to IDA | IDA clearance of TOR and Cost estimate | Transmit EOI for Publication to WB and Publication by PIU | REOI (Closing Date) | Transmit Shortlist (ER + RFP) to IDA | IDA Clearance of short-list and RFP | Issue of RFP | Opening of RFP (Technical Proposal) | Transmit the TER (Technical Evaluation Report) to IDA | IDA Clearance of TER | Opening of Financial Proposal | Transmit CER (Combined Evaluation Report), Negotiation - Draft Contract to IDA | IDA clearance of draft contract | Clerance by CA | Signing of Contract | Mobilization of Contract | Contract Completion Date | Name of Contractor/Nationality& zip code | Contract Value | Expenditure Incurred to Date |  | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 15 | 9 | 10 | 11 | 12 | 13 | 14 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Planned |  |  |  | Development & Maintenance of Web Based Portal & MIS for M&E of VTIP | 490000 | QCBS | Prior | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | October 2009 | October 2009 | December 2009 | December 2009 | 2 Years from award of contract | M/s Wipro Ltd. | Rs. 1.98 Crore (Approx) | Nil
Revised
Actual
2 | Planned |  |  |  | Hiring of Individual Procurement Specialist | 35000 | Hiring of Individual | Post | Completed | Completed | Completed | Completed | Completed | [10 empty] | December 2009 | January 2010 | 1 year from award of contract
Revised
Actual
3 | Planned |  |  |  | Hiring of Individual Environment / Civil Work Specialist | 35000 | Hiring of Individual | Post | Completed | Completed | Completed | Completed | Completed | [10 empty] | December 2009 | January 2010 | 1 year from award of contract
Revised
Actual
4 | Planned |  |  |  | Hiring of Services of Data Centre | 43500 | SSS | Post | December 2009 | [6 empty] | February 2010 | February 2010 |  |  | March 2010 |  |  |  | May 2010 | May 2010 | Renewable every year
Revised
Actual
5 | Planned |  |  |  | Hiring of Management Consultant to assist NPIU for Development of MIS Software | 50000 | SSS | Post | Completed |  | Completed |  |  |  |  | November 2009 | December 2009 | December 2009 |  | December 2009 |  |  |  | January 2010 | January 2010 | 1 year from award of contract | Not Yet Finalised | Not Yet Finalised | Nil
Revised
Actual
6 | Planned |  |  |  | Hiring of Project Implementation Consulting Firm | 1087000 | QCBS | Prior | December 2009 | January 2010 |  | January 2010 |  | February 2010 |  | February 2010 | March 2010 | April 2010 | April 2010 | May 2010 | May 2010 | June 2010 |  | July 2010 | August 2010 | 2 year from award of contract
Revised
Actual